## Read Me
Read Me
This workbook governs how your business adopts and tracks AI. Do not treat it as optional.
Four worksheets. Four simple steps.
Step 1: AI Inventory
Know what AI tools are in use. Right now. Complete in 30 days. Distribute the template to IT, Finance, Operations, and Compliance. Most organisations discover 2–3x more tools than they thought existed.
Step 2: Investment Gate
No AI project over £50k gets funded without a one-page business case. Three questions only: What problem are you solving? What does the current state cost? What is the net benefit in pounds? If a sponsor cannot answer these on one slide, the project is not ready.
Step 3: Ownership Model
Three names per major project. A Business Owner accountable for results. A Data Owner accountable for quality. A Risk Owner accountable for compliance. Write the names down. Ambiguity is where shadow AI thrives.
Step 4: Monthly Tracking
Track actual vs. forecast benefit and cost every month. If you spent £1m, you check results monthly—not in 18 months. Use RAG status (Red / Amber / Green) to flag issues early.
Who Does What
FD: Owns the investment gate and monthly tracking. Sign off numbers. Challenge assumptions.
MD: Back the FD publicly. No AI spend without the one-slide business case. That is the rule.
Business Owner: Updates monthly. Answers the simple question: are we winning?
Risk/Compliance: Signs off Step 3 ownership model. Flags data and regulatory risks in Step 1.
Timeline
Month 1: Complete Step 1 (inventory).
Month 2: Use Step 2 for new proposals.
Month 3 onwards: Update Step 4 monthly.

## Step 1 - AI Inventory
Tool | Team | Users | Process | Data Inputs | Risks
ChatGPT | Finance | 3 | Drafting commentary on monthly management accounts | Customer names, high-level performance summaries | Risk of confidential financial commentary being stored on external servers
Microsoft Copilot | Sales | 15 | Drafting customer emails and proposals | Customer contact details, pricing options | Potential exposure of customer data to cloud AI service; need DPA review
ForecastPro AI | Operations | 5 | Generating weekly volume forecasts | Historical order data, SKU-level demand | Model assumptions not validated; forecasts used for purchase commitments
LegalGPT SaaS | Legal | 2 | Summarising supplier contracts | Full contract texts, supplier names, pricing terms | Contracts uploaded to US-hosted tool; unclear data retention policy
SupportBot AI | Customer Service | 10 | Suggesting responses to support tickets | Customer emails, ticket history | Possible inclusion of special category data (health notes) in prompts

## Step 2 - Investment Gate
Project | Problem qualtified | Baseline | Baseline costs p/a | Expected benefits p/a | New costs p/a | Implementation costs (one-off) | Payback (months) | Owner
AP Automation AI | Reduce invoice cycle from 5 days to 1; cut manual touchpoints by 60% | 4 FTE processing 2,000 invoices/month; frequent late payment penalties | 160000 | 90000 | 30000 | 80000 | 18 | Finance Director
Churn Prediction Model | Reduce monthly customer churn from 5% to 3% | Manual churn analysis; retention offers applied inconsistently; no early warning | 0 (no dedicated team, but lost revenue ~£250k/year) | 150000 | 50000 | 120000 | 16 | Commercial Director
AI Sales Assistant | Increase win rate on qualified opportunities from 25% to 30% | Sales reps write all emails manually; limited time for follow-up | 0 (time buried in existing roles) | 200000 | 70000 | 60000 | 10 | Sales Director
Demand Forecasting Tool | Improve forecast accuracy by 15 percentage points | Chronic overstock and stockouts; write-offs ~£100k/year; expediting costs ~£80k/year | 180000 | 120000 | 40000 | 100000 | 20 | Operations Director

## Step 3 - Ownershipe Model
Project | Project Owner | Project Owner Role | Project Accountability | Data Owner | Data Owner Role | Data Accountability | Risk Owner | Risk Owner Role | Risk Accountability | Key Risks
AP Automation AI | Sarah Brown | Finance Director | Deliver target reduction in processing time and FTE; stop project if ROI not achieved | James Patel | Financial Controller | Define invoice data standards; ensure clean, complete data feeding the model | Helen Brooks | Head of Risk & Compliance | Review vendor, DPA, and control environment; sign off on go-live and major changes | Exposure of supplier bank details; need clear access controls and audit trail
Churn Prediction Model | Mark Evans | Commercial Director | Own churn reduction target; embed model outputs into retention processes | Laura Green | Head of Data & Analytics | Own data pipeline, feature set, and data quality checks | Tom Riley | Company Secretary | Assess fairness and bias, especially for vulnerable customers; oversee documentation | Risk of profiling complaints; need clear opt-out and explanation of decisions
Demand Forecasting Tool | Rachel Smith | Operations Director | Hit stock and service-level targets using AI forecasts | Emily Shaw | Supply Chain Analyst | Maintain master data (SKUs, lead times, suppliers); monitor forecast accuracy | David Turner | CFO | Ensure financial impact is tracked and reported; review model risk where forecasts drive large commitments | Over-reliance on model for large purchasing decisions; need manual override rules

## Step 4 - Monthly Tracking
Project | Month | Benefits Status | Expected Benefit (year) | Expected Costs (year) | Actual Benefits (month) | Actual Costs (month) | Actual Benefits (YTD) | Actual Costs (YTD) | Key Changes In Usage, Cost, Data or Risk
AP Automation AI | 2026-03 | Amber | 90000 | 30000 | 6500 | 2100 | 18500 | 6200 | Adoption at 70% of invoices; two suppliers still on manual process; minor data quality issues identified and fixed
Churn Prediction Model | 2026-03 | Green | 150000 | 50000 | 10000 | 4200 | 26000 | 11500 | Model live for broadband segment only; early signs of improved save rate; additional data sources being integrated
Demand Forecasting Tool | 2026-03 | Red | 120000 | 40000 | -5000 | 3100 | -8000 | 9200 | Forecasts led to over-ordering on two key SKUs; governance updated to require planner review on exceptions >20%
AI Sales Assistant | 2026-03 | Amber | 200000 | 70000 | 7500 | 3500 | 19000 | 9800 | Usage high in new logo team, low in account management; training session scheduled; refining prompts to reduce low-value suggestions